UCL Global alumni groups - **event checklist**

**Pre-event**

|  |  |  |  |
| --- | --- | --- | --- |
| **Task** | **Time before event** | **Responsibility** (*to be populated by group*) | **Completed?** |
| Agree concept and secure speakers / venue  | 6 weeks |  |[ ]
| Notify AR contact of activity details, including if online / in-person | 6 weeks |  |[ ]
| Event email content drafted and shared with AR contact, including any imagery | 4 weeks |  |[ ]
| Post on [UCL Bentham Connect](https://uclbenthamconnect.com/) and other relevant social channels promoting event  | 1 x 4 weeks1 x 2 weeks1 x 1 week |  |[ ]
| Run sheet finalised, including agreement of responsibilities | 2 weeks |  |[ ]
| Speaker briefing completed and shared (if relevant) | 2 weeks |  |[ ]
| Slides created / speaker slides received | 1 week |  |[ ]
| 15-minute pre-event catch up call with UCL contact | 1 week |  |[ ]
| Pre-event huddle: tech check, run sheet check, answer speaker questions | 30 mins |  |[ ]

**Event**

|  |  |  |  |
| --- | --- | --- | --- |
| **Task** | **Timings** | **Responsibility**(*to be populated by group*) | **Completed?** |
| Pre-event huddle: tech check, run sheet check, answer speaker questions | 30 mins pre-event |  |[ ]
| Screensharing of relevant content e.g. slides, video | Throughout |  |[ ]
| Reg list - check off names(Zoom: admit attendees in waiting room) | Event start |  |[ ]
| Deliver event according to run sheet | Throughout | All |[ ]

**Post-event**

|  |  |  |  |
| --- | --- | --- | --- |
| **Task** | **Time after event** | **Responsibility**(*to be populated by group*) | **Completed?** |
| Share attendee list and overview of event with UCL contact  | 1 day |  |[ ]
| Thank you email content to attendees shared with UCL contact | 1 day |  |[ ]
| Complete expenses form and share with UCL contact (if relevant) | 1 week |  |[ ]