## Introduction
e-HIT Case Study: Community Nursing Information System (CNIS)
We studied a Community Nursing Information System (CNIS) in one Health Board in Scotland. The CNIS was designed to provide an electronic patient record system for District Nurses to enable them to record and deliver information to support the delivery of care to patients, and to interface with and share information with associated agencies, particularly Social Services. A web-based electronic system in conjunction with a hand held mobile device (iPAQ) enabled staff to gather and share information electronically. Continue through the rest of the toolkit to see how the CNIS scored.
Next page
Toolkit
Report
Introduction
e-HIT Case Study: CNIS

## Context1
Policy
National policy | This intervention is completely at odds with current or planned national policy. |  | This intervention is entirely compatible with current and planned national policy.
10
The CNIS was developed in response to the NHS in Scotland Information Strategy.
| This intervention will hinder the achievement of nationally directed priorities or targets. |  | This intervention will enable the achievement of nationally directed priorities or targets.
7
The CNIS was developed in response to national directives to introduce electronic patient records and to support the easy transfer of referral and reporting data between the Trust and other agencies.
Local policy | This intervention is completely at odds with current or planned local policies. |  | This intervention is entirely compatible with all current and planned local policies.
10
The CNIS is in line with the Information and Technology Strategy of the Trust and Health Board which is to introduce electronic records and information sharing between agencies.
Context (1)
No man is an island, and neither is any NHS organisation. Before deciding whether or not to implement a new intervention, it is worth considering the overall context, and in particular, how well the intervention will fit with organisational priorities and structures. In turn, these are often influenced by national policies.
Next page
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Toolkit
Report
Introduction
e-HIT Case Study: CNIS

## Context2
Culture
Local culture | The organisational culture is reluctant to adopt e-health initiatives and dreads change. |  | The organisational culture welcomes e-health initiatives and embraces change.
7
There were conflicting attributes: Although the PCT and District Nurse managers welcomed this initiative, the organisation as a whole had experience of a series of failed attempts to introduce electronic records, and there were a number of concurrent organisational changes and policy initiatives leading to change fatigue.
| The multiple staff groups likely to be involved in implementing the e-health initiative have poor working relationships and poor communication with no history of problem solving and co-operation. |  | The multiple staff groups likely to be involved in implementing the e-health initiative have good working relationships and good communication with a history of problem solving and co-operation.
7
Working relationships between key partners were facilitated by the existence of joint Community Health and Social Care Partnerships, with a history of good joint working. Good working relationships and communication existed between Senior Nurse managers, the IT department and clinical staff.
| There is no local sponsor, or the local sponsor is not well respected, or is likely to devote insufficient time and energy to promoting the implementation. |  | The intervention is strongly supported by a well-respected local sponsor who will provide the time and energy needed to promote the implementation.
8
The CNIS was strongly supported by the General Manager. An initial Implementation Group was an active champion for the intervention, but has become defunct, causing problems in the latter stages of the rollout.
| There are particular opinion leaders within the organisation who are likely to oppose implementation of this e-health initiative. |  | There are particular opinion leaders within the organisation who are likely to support the implementation of this e-health initiative.
10
There were a number of senior opinion leaders championing this initiative.
Context (2)
Next page
Go back
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Toolkit
Report
Introduction
e-HIT Case Study: CNIS

## Context3
Resources and risk
Resources | The organisation is under resourced, and cannot fully meet the costs and additional workload resulting from the implementation of this e-health initiative, including e.g. training, on-going support, contingencies, publicity. |  | The organisation is well resourced, and can fully meet the costs and additional workload resulting from the implementation of this e-health initiative, including e.g. training, on-going support, contingencies, publicity.
6.5
Score of 6.5 because 8 in one sector, 5 in the other. Implementation in one sector was well resourced, but in the other financial resources were inadequate which hindered electronic sharing of the Single Shared Assessment documentation between the two sectors, thus preventing realisation of the benefits in both sectors.
| The e-health initiative is likely to disrupt the existing allocation of resources or the formal or informal norms by which they are allocated. |  | The e-health initiative will make no change to existing allocation of resources or the formal or informal norms governing allocation of resources.
10
This was true.
Risk | The proposed intervention is completely at odds with the organisation’s existing risk management policies. |  | The proposed intervention is entirely compatible with the organisation’s existing risk management policies.
10
The intervention is likely to enhance record keeping and record access by staff delivering patient care and therefore is likely to reduce risk for staff and patients.
Context (3)
Next page
Go back
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Toolkit
Report
Introduction
e-HIT Case Study: CNIS

## Intervention
Intervention
Impact on clinical practice | The e-health initiative will disrupt health professional – patient interactions. E.g. it will make them slower, or introduce tasks inappropriate to the encounter. |  | The e-health initiative will facilitate health professional – patient interactions. E.g. it improves communication within consultations, or enables faster completion of the key objectives of health care interactions.
8
The electronic patient record and assessment did not appear to disrupt the nurse-patient interaction. Nurses used their judgement to decide whether or not to enter the information into the hand held mobile device in the patient’s home or shortly after the visit in the car.
| There are serious concerns about the reliability, security and confidentiality of the intervention. |  | The intervention is entirely credible in terms of security, confidentiality and reliability.
10
All senior managers were satisfied with the system’s security, confidentiality and reliability.
Ease of use of the system | The e-health initiative is difficult to use, or does not do what it’s supposed to do. |  | The e-health initiative is easy to use and fit for purpose.
10
The design process included extensive consultation with end-users, and the system was adapted to fit local needs and work patterns. On-going adaptation is built into the system and implementation programme.
Effectiveness and cost-effectiveness | The e-health initiative has not been evaluated nor demonstrated to improve health care in a cost-effective manner. |  | The e-health initiative has been well evaluated and has been demonstrated to improve health care in a cost-effective manner.
6
The system was piloted. The pilot identified various problems which mediated against the likely improvement to health care / information sharing, and these problems were addressed prior to the main implementation.
The Intervention
The nature of the intervention is likely to be a key factor in whether it is successfully integrated into routine practice or not.
Next page
Go back
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Toolkit
Report
Introduction
e-HIT Case Study: CNIS

## Workforce
Workflow and training
Impact on work and workflow | There is likely to be a period of considerable increased workload during the implementation. |  | There is unlikely to be any period of increased workload during the implementation.
2
There was initially a duplicate system of record keeping running until the written records have been transferred to the electronic system and only minimal additional resources to cover this additional workload were provided.
| The intervention will disrupt existing work patterns and make them less efficient. |  | The intervention will increase the efficiency of current work patterns.
7
The intervention had both pros and cons: it took longer to complete the nursing assessment than the old paper based system, but reduced staff time spent in chasing notes, and enabled all appropriate staff to access up-to-date patient records in the community, making work more efficient.
| The intervention will substantially disrupt current divisions of labour between staff groups. |  | The intervention is completely compatible with current divisions of labour.
10
The intervention did not disrupt existing divisions of labour.
Education and training | All staff who will use the proposed initiative will need very substantial training prior to use. |  | No training will be needed by any staff group prior to implementation of the initiative.
8
Extensive training was provided for the district nursing teams.
The workforce, including the various professional groups who are going to have to use the new intervention are crucial in determining whether the intervention becomes embedded into routine practice, or whether it is merely imposed. People may “adopt” a technology – i.e. use it, however much it disrupts their work, if the incentives for use, or the penalties for non-use, are sufficient. Once these incentives or penalties are removed however, they are likely to stop using it. In contrast, a technology that has become “normalised”, or part of routine use, will continue to be used even after the incentive structure has been dismantled.
Next page
Go back
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Toolkit
Report
Introduction
e-HIT Case Study: CNIS
The workforce - people and work patterns (1)

## Workforce2
Relationships
Relationships between different professional groups | The proposed intervention will substantially disrupt existing power relationships between different staff groups. |  | The proposed intervention is entirely compatible with existing power relationships between different staff groups.
10
There was no direct impact on power relationships between staff groups by this intervention.
| The intervention will undermine confidence about each other’s expertise and performance between different professional groups. |  | The intervention will enhance confidence about each other’s expertise and performance between different professional groups.
10
The intervention could have a significant positive impact: sharing a common, Single Shared Assessment document enabled social service staff and health care staff to see what each other had done; not doing the work on IT systems in both sectors concurrently has prevented full realisation of this benefit.
| Responsibility and accountability are not aligned, i.e. different staff groups have responsibility for how the intervention is used, and accountability for the outcome of the intervention. |  | Responsibility and accountability are fully aligned i.e. one staff group is both responsible for how the intervention is used and accountable for the outcome of the intervention.
10
Responsibility and accountability were aligned.
The workforce - people and work patterns (2)
Report
Go back
Context (1)
Context (2)
Context (3)
Intervention
Workforce (1)
Workforce (2)
Toolkit
Report
Introduction
e-HIT Case Study: CNIS

## Scores
Summary of Topic Scores
Context | 85.5%
The intervention | 85%
The workforce | 81.43%
Context
National policy | Compatibility with current and planned national policy | 10
| Enabling the achievement of national priorities or targets | 7
Local policy | Compatibility with current and planned local policy | 10
Local culture | Welcoming e-health / embracing change | 7
| Good working relationships | 7
| Supported by a well-respected local sponsor | 8
| Supported by opinion leaders | 10
Resources | Well resourced | 6.5
| Minimal impact on resource allocation | 10
Risk | Compatibility with existing risk management policies | 10
85.5
The Intervention
Impact on clinical practice | Facilitation of health professional - patient interactions | 8
| Security, confidentiality and reliability | 10
Ease of use of the system |  | 10
Effectiveness and cost-effectiveness |  | 6
34
The workforce - people and work patterns
Impact on work and workflow | Not increasing staff workloads | 2
| Increasing efficiency of work patterns | 7
| Compatibility with divisions of labour | 10
Education and training | Minimal training needed | 8
Relationships between different professional groups | Compatibility with existing power relationships | 10
| Enhancing confidence between groups | 10
| Alignment of responsibility and accountability | 10
57
Summary
Context | 85.5%
The intervention | 85%
The workforce | 81.43%
Summary of Scores
These scores are subjective and only a guide, however, the higher the scores, the more likely that the intervention will normalise.
Next page
Toolkit
Report
Introduction
e-HIT Case Study: CNIS
Summary of Scores
Summary of Comments
Verdict: The Community Nursing Information System (CNIS) had normalised to some degree across the Trust. This appears to have been due to: • Strong leadership with good clinical buy-in; • An implementation process designed to run over 3 years with recurring funding. • A system that was purchased externally, developed and adapted internally in response to changing end-user requirements; • A dedicated IT training and support team with a Lead Project Nurse who was a qualified District Nurse; • Small group/team training and individual support provided at nurses’ own bases; • The use of a web-based electronic system in conjunction with mobile, hand held devices (iPAQs) ensuring up-to-date patient information that was easily accessible. • The ability to populate the Single Shared Assessment documentation with data from the Nursing Assessment using a simple a trigger button. These factors outweighed problems in the implementation, including: • A slow roll-out process; • Clinicians with little experience of using electronic systems; • The 2 sectors not developing the systems in tandem; • Considerable concurrent organisational change. As the roll-out of the CNIS is not yet complete the degree of normalisation across the Trust is variable. The full realisation of the benefits of this system will materialise when: • All staff across the Trust are trained actively using the system • the Single Shared Assessment documentation can be electronically transferred back and forth between health and social care systems. However, • the CNIS and electronic patient records incorporating the Single Shared Assessment documentation has been widely accepted as a useful and desirable e-Health initiative by managers and clinicians alike; • staff can readily appreciate the likely benefits to patient care; • managers can see it’s value in terms of clinical audit, standards and management reporting functions.

## Comments
Context
Topic | Sub-topic | Score | Comments
National policy | Compatibility with current and planned national policy | 10 | The CNIS was developed in response to the NHS in Scotland Information Strategy.
| Enabling the achievement of national priorities or targets | 7 | The CNIS was developed in response to national directives to introduce electronic patient records and to support the easy transfer of referral and reporting data between the Trust and other agencies.
Local policy | Compatibility with current and planned local policy | 10 | The CNIS is in line with the Information and Technology Strategy of the Trust and Health Board which is to introduce electronic records and information sharing between agencies.
Local culture | Welcoming e-health / embracing change | 7 | There were conflicting attributes: Although the PCT and District Nurse managers welcomed this initiative, the organisation as a whole had experience of a series of failed attempts to introduce electronic records, and there were a number of concurrent organisational changes and policy initiatives leading to change fatigue.
| Good working relationships | 7 | Working relationships between key partners were facilitated by the existence of joint Community Health and Social Care Partnerships, with a history of good joint working. Good working relationships and communication existed between Senior Nurse managers, the IT department and clinical staff.
| Supported by a well-respected local sponsor | 8 | The CNIS was strongly supported by the General Manager. An initial Implementation Group was an active champion for the intervention, but has become defunct, causing problems in the latter stages of the rollout.
| Supported by opinion leaders | 10 | There were a number of senior opinion leaders championing this initiative.
Resources | Well resourced | 6.5 | Score of 6.5 because 8 in one sector, 5 in the other. Implementation in one sector was well resourced, but in the other financial resources were inadequate which hindered electronic sharing of the Single Shared Assessment documentation between the two sectors, thus preventing realisation of the benefits in both sectors.
| Minimal impact on resource allocation | 10 | This was true.
Risk | Compatibility with existing risk management policies | 10 | The intervention is likely to enhance record keeping and record access by staff delivering patient care and therefore is likely to reduce risk for staff and patients.
The Intervention
Impact on clinical practice | Facilitation of health professional - patient interactions | 8 | The electronic patient record and assessment did not appear to disrupt the nurse-patient interaction. Nurses used their judgement to decide whether or not to enter the information into the hand held mobile device in the patient’s home or shortly after the visit in the car.
| Security, confidentiality and reliability | 10 | All senior managers were satisfied with the system’s security, confidentiality and reliability.
Ease of use of the system |  | 10 | The design process included extensive consultation with end-users, and the system was adapted to fit local needs and work patterns. On-going adaptation is built into the system and implementation programme.
Effectiveness and cost-effectiveness |  | 6 | The system was piloted. The pilot identified various problems which mediated against the likely improvement to health care / information sharing, and these problems were addressed prior to the main implementation.
The workforce - people and work patterns
Impact on work and workflow | Not increasing staff workloads | 2 | There was initially a duplicate system of record keeping running until the written records have been transferred to the electronic system and only minimal additional resources to cover this additional workload were provided.
| Increasing efficiency of work patterns | 7 | The intervention had both pros and cons: it took longer to complete the nursing assessment than the old paper based system, but reduced staff time spent in chasing notes, and enabled all appropriate staff to access up-to-date patient records in the community, making work more efficient.
| Compatibility with divisions of labour | 10 | The intervention did not disrupt existing divisions of labour.
Education and training | Minimal training needed | 8 | Extensive training was provided for the district nursing teams.
Relationships between different professional groups | Compatibility with existing power relationships | 10 | There was no direct impact on power relationships between staff groups by this intervention.
| Enhancing confidence between groups | 10 | The intervention could have a significant positive impact: sharing a common, Single Shared Assessment document enabled social service staff and health care staff to see what each other had done; not doing the work on IT systems in both sectors concurrently has prevented full realisation of this benefit.
| Alignment of responsibility and accountability | 10 | Responsibility and accountability were aligned.
Summary of Comments
Go back
Toolkit
Report
Introduction
e-HIT Case Study: CNIS
Summary of Scores
Summary of Comments