## Sheet1
Category |  | Issue Name | Detail | Impact | Recommendation
Contractors | Problem | Contract Requirements | The PM was not fully engaged in the contract process. | All requirements were not included in the initial contract award. A contract modification was required which added a week to the project. | PM must be fully engaged in all contract processes. This must be communicated to both PM and contract personnel.
The lessons learned from UCL projects are categorised by project knowledge area and descriptions, impacts These lessons are categorized by project knowledge area and descriptions, impacts, and recommendations are provided for consideration on similar future new construction projects. It is important to note that not only failures or shortcomings are included but successes as well.
Please use te drop down where applicable