## Stage Gate Checklist
SMP Stage Gate Checklist
Unique Project Ref
Project Title
Building(s)
UCL Project Officer (UPO)
Stage Gate 1
Item | Evidence | Required
PID/PAR | Link
Stage Gate 2
Item | Evidence | Required
Business Case | Link
Programme
Monthly Report | Link
Cost Plan
Project Tracker
Risk Risk Register
Project Stake Holder Directory | Link
Fire Safety Requirements | Link
Property Checklist | Link
PEP | Link - in folder | If applicable
Pedestrian and Traffic Flows | Link
CDM Form 2 | Link
Stage Gate 3
Item | Evidence | Required
Specifications of Works | Link
BREEM/Ska/Mini-Ska Review
Updated Carbon Tool |  | If applicable
Stage Gate 4
Item | Evidence | Required
Updated Business Case | Link - in folder | If applicable
Value Engineering Report | Link | If requested
Monthly Report | Link
Cost Plan
Project Tracker
Risk Risk Register
Construction Programme | Link - in folder | If applicable
CDM Form 2 | Link
CH1 Form | Link
CH2 Form | Link
Project Insuance Form | Link
Project Stake Holder Directory | Link
Tender Request Form | Link
Tender Return Form | Link
Tender Evaluation Report | Link - in folder
LOI Request Form | Link | If applicable
Stage Gate 5
Item | Evidence | Required
Handover Plan | Please use this box to confirm that Transition Team are aware and have engaged as applicable. Inc updating Building User Guide if applicable. | If applicable
CDM Form 2 | Link
Fire Safety Requirements (Handover) | Link
O&M Manuals | Link - in folder
CH3 Form | Sustainability - Link | Where applicable
| Water Systems - Link | Where applicable
| Mechanical Systems - Link | Where applicable
| Lifts - Link | Where applicable
| AC & Ventilation - Link | Where applicable
| Building Fabric - Link | Where applicable
| Electrical Systems - Link | Where applicable
| Facilities - Link | Where applicable
| Security - Link | Where applicable
| BMS - Link | Where applicable
| Misc - Link | Where applicable

## Specifications of Work
Specifications of Work
Return to main page
Please use the text box below to highlight the specifications of work. If there are drawings that are included, please indicate this and ensure these drawings are in your project folder.

## Project Stakeholder Directory
Project Stakeholder Directory
Return to main page
Name | Organisation | Project Role | Responsibilities | Email | Tel | Address
Project Team
Project Sponsor/ Academic Lead
Estates Strategy Manager
UCL Project Officer
External PM
Senior Project Manager
Consultant Team
Architect
Partner
Cost Manager
Associate
Project Surveyor
Building Services
Project Director
Senior Mechanical Engineer
Senior Electrical Engineer
Team Leads
EM&I
Environment
Safety
Satellite Services
Facilities
Fire Officers
ISD
Operator/Users
Neighbours
Return to main page

## Fire Safety Requirements
Fire Safety Requirements
Return to main page
Fire Safety Technical notes available to download from www.ucl.ac.uk/fire/documents
1 | Stage 2 (B & C): Initiation (To be reviewed at each stage) |  | Yes | No
1.1 | Has the UCL Fire Safety Manager been provided with a Project overview?
1.2 | If new building / property acquisition - has fire safety due diligence survey been undertaken?
1.3 | Has a Stage 2/C fire strategy and/or fire risk assessment been developed based on the project brief?
1.4 | Is the project increasing the premises occupancy level? If Yes, has an initial stair and floor occupancy calculations been undertaken?
1.5 | Is Fire Engineering support required with a need to appoint Consultants, due to complexity? (Discuss first with UCL Fire Safety Manager)
1.6 | Has UCL Fire Safety Employers' Requirements (UCL Fire Safety Technical Notes) been issued to the Architect & MEP design team?
2 | Stage 3 (D & E): Project Design Development (To be reviewed at each stage) |  | Yes | No
2.1 | Will the Project be undertaken with UCL staff, students & visitors in occupation during building works - is a decant phasing programming or strategy provided for scheme and during works to include potential impact on surrounding buildings (fire spread, evacuation etc.) to ensure safety of occupants - If YES Design Team to work through impact assessments & provide details and mitigation in project fire risk assessment / fire strategy provision for consideration by Principle Contractor when tendering
2.2 | Are fire fighting shafts and other fire brigade facilities required or need to been considered?
2.3 | Are fire sprinklers required or need to been considered?
2.4 | Has an Evacuation Lift been considered as part of the inclusive design & MEP strategy? Separate sprinklers and from fire fighting facilities - Refer to fire fighting shafts / lifts rather than just lifts and more encompassing.
2.5 | Has there been consultation with a Fire Engineer (if provided), Building Control & UCL Fire Safety Manager by the Architectural design team?
2.6 | Has there been consultation with the Fire Engineer (if provided), Building Control & UCL Fire Safety Manager by the M&E / MEP design team?
2.7 | Has a 'Stage 3/D' fire strategy report been published?
3 | Stage 4 (F/G/H): Procurement & Planning (To be reviewed at each stage) |  | Yes | No
3.1. | All Contracts - has the required fire safety instructions been issued with tender documentation including named fire safety point of contact, fire strategy, fire phasing & mitigation docs and mandatory passive fire protection and fire stopping required through UCL framework contractor (UCL Fire MI06/TN066), Fire & Safety of Hoardings (MI07) and UCL Waste Management (fire safety) requirements (MI08).
3.2 | D&B Contract - has there been consultation with Appointed Contractor's architectural design team & check on project fire safety provision?
3.3 | D&B Contract - has there been consultation with Appointed Contactor's M&E / MEP design team & check on project fire safety provision?
4 | Stage 5 (J & K): Implementation (To be reviewed at each stage) |  | Yes | No
4.1 | Has the 'Principle Contractor (PC)' provided a project works fire strategy & fire risk assessment agreed with the UCL Fire Safety Manager ?
4.2 | Mobilisation - prior to starting project works PC decant phasing programming &/or strategy to be agreed and impact mitigation documented with UCL Fire Safety Manager
4.3 | Mobilisation - at site set up & prior to starting works, local fire / safety / fire logistics Toolbox Talk with PC site manager & their safety reps with UCL fire & safety staff
4.4 | Fire Brigade - will fire brigade equipment and facilities be impacted by the works - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision?
4.5 | Fire Brigade - will any rendezvous points for fire services & access to main fire alarm panel been impacted - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision?
4.6 | Fire Brigade - will any fire hydrants be disabled or made inaccessible - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision?
4.7 | Fire Brigade - will any fire service vehicle access be modified, narrowed or blocked - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision?
4.8 | Will any fire fighting / fireman's lifts, dry risers, hose reels, pumps or others be disabled or made inaccessible - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision?
4.9 | Has any Fire Assembly Areas been made smaller or be obstructed by construction compounds? - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision?
4.10 | Is the project going to impact on the operation of existing fire alarm and detection systems, including Emergency Voice Communication (EVC) System; does it have means to raise an alarm with UCL Security Control Room? - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision?
4.11 | Is the project going to generate high fire risks during construction (e.g. highly combustible materials, ignition sources such as hot welding, hazardous processes or storage of hazardous materials, LPG or similar) - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision? (Note - Acetylene is prohibited on site)
4.12 | Escape Routes - will any of the escape routes been impacted (in project building &/or other building stairs & exits etc.) by any works carried out in corridors, stair enclosures, lobbies and vestibules, emergency lighting, that impact on occupants evacuating from the premises safely along these routes? - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision / What arrangements for change process for informing users and other relevant persons of alterations?
4.13 | Escape Routes - will the escape routes from the building (or other buildings) to Fire Assemble areas be made narrower or no longer be available (e.g. through construction vehicle access, waste storage, temporary hoists etc.) - If YES work through the impact and provide detail / mitigation in project fire risk assessment and fire strategy provision?
4.14 | Fire Compartmentation - will any of the fire compartmentation / external fire spread / separating project areas be modified or be impacted on during construction? - If YES work through the impact and provide detail / mitigation in project fire risk assessment internal and external fire spread strategy provision?
5 | Stage 6 (L): Operations (To be reviewed at each stage) |  | Yes | No
5.1 | Regulation 38 (The Building Regulations) - provision of Fire Safety information PRIOR to building occupation by UCL
5.2 | General fire safety inspections - provision of fire extinguishers and fire signage etc.
5.3 | Fire alarm (including EVC / DMS systems / signals back to UCL security control room) - commissioning / UCL fire safety staff to witness
5.4 | Emergency lighting - commissioning
5.5 | Fire brigade equipment and facilities (Fire Lifts / Dry Risers / Smoke Control) - commissioning / UCL fire safety staff to witness
5.6 | Fire brigade equipment and facilities - commissioning / UCL fire safety staff to witness
5.7 | Occupants / staff moving into premises to have initial fire safety familiarisation walk through (MI03)
Completion (signed off by) |  | Project Officer: ………………………………….. Date: …………………………………..
Completion (signed off by) |  | UCL Fire Safety Manager: ………………………………….. Date: …………………..
NOTE - SEPARATE SHEET FOR FIRE SAFETY HANDOVER CHECK SHEET
Documents assisting review to be provided by the central campus team:
> Bloomsbury Campus Masterplan Fire Strategy Report (where appropriate); > All projects - UCL Fire Safety Technical Notes forming part of the Employer's Required (ER's) issued at Stage 3(C) & implemented at Stage 4(D) Design;
Documents to be provided to be provided by the External Project Manager:
Project Phasing layouts indicating: - Marking up of any fire item becoming modified or unavailable; - Any specific mitigation provisions to be put in place to enable UCL to continue occupying their site safety in compliance with the Fire Safety Order; - Availability of the fire alarm and detection systems in public and construction areas; - Temporary escape stairs; - Temporary fire separations; - Fire & safety hoarding provision; - Fire separation from waste and site storage & activities
Completion (signed off by) |  | Project Officer: ………………………………….. Date: …………………………………..
Return to main page

## Property Checklist
Property Checklist
Property related matters to consider during the design and planning
Question | Response
1. Is Landlords Consent required?
2. Will the use comply with the user clause?
3. What is the length of lease remaining? Is it sufficient to justify refurbishment expenditure?
4. What is the future reinstatement liability?
5. Will neighbours’ rights of light be injured by UCL’s scheme or taken specific advice?
6. Has the landlords licence been received (as if not it could affect a forthcoming rent review)?
7. Does the work affect the Rateable value?
8. Is planning permission required? If yes, give key dates for approval.
Return to main page

## Traffic and Pedestrian Flows
Traffic and Pedestrian Flows
Stage 2: Initiation (To be reviewed at each stage)
1.1 | How many UCL users will need to be relocated by the project delivery
1.2 | Please state what type of use is the facility
|  | Yes | No
1.3 | Please state where the UCL users will be relocated
1.4 | Will the project delivery / waste removal be share with the Campus pedestrian thoroughfare
1.5 | Will the project impact / blocked any of the Campus pedestrian thoroughfare If YES to be highlighted on a project phasing layout
Return to main page

## CDM Form 2
CDM Form 2
Return to main page
1 | Stage 1: Need Stage | Notes/Date Completed
1.1 | Confirm that relevant pre-construction information (including environmental and interface risks) is provided to the team reviewing the feasibility.
1.2 | Consider who would be the most appropriate to take the Principal Designers Appointment and discuss with the design team.
1.3 | Confirm the proposed program allows enough time for design, planning and construction including time for the contractor to plan and prepare for the work, and mobilise for the start of the construction phase.
Completion (signed off by)
University Project Officer: ………………………………….. Date: …………………………………..
2 | Stage 2: Initiation Stage (Planning Application/Approval Stage) | Notes/Date Completed
2.1 | Confirm a "Principal Designer" has been appointed in writing. (where we don't appoint UCL must complete the Principal Designers duties)
2.2 | Confirm all appointments (Principal Designers, Designers, Contractors) have the skills, knowledge and experience to identify, reduce and manage health and safety risks.
2.3 | Confirm the Principal Designer has visited the proposed construction site area so that existing health and safety hazards and site constraints can be identified for inclusion in the Pre-construction information to ensure the design team and contractor can address accordingly
2.4 | Confirm in writing what relevant pre-construction information (including environmental and interface risks) is required to be provided to the design team and contractors
2.5 | Confirm the “initial” investigations/surveys have been identified, any existing health and safety file received, and this information been received by the Principal Designer and the design team.
2.6 | Confirm the proposed program allows enough time for design, planning and construction including time for the contractor to plan and prepare for the work, and mobilise for the start of the construction phase.
Completion (signed off by)
University Project Officer: ………………………………….. Date: …………………………………..
3 | Stage 3: Design Development | Date completed
3.1 | Confirm “all necessary” investigations and surveys been completed (e.g. refurbishment and demolition asbestos survey, soil investigation, existing utility services, lead paint, anthrax etc.) and this information has been provided to the Principal Designer and the design team.
3.2 | Confirm that the scope of the asbestos survey information (refurbishment & demolition and/or management) addresses all the proposed contractor working areas, i.e. main site area, all associated services routes, roof, plant rooms etc.
3.3 | Confirm the design (where applicable - a new workplace or alterations to an existing workplace ) complies with the Workplace (Health, Safety & Welfare) Regulations 1992.
3.4 | Ensure the design considers the impact on students, staff and visitors from the construction area and protects them from the risks.
Completion (signed off by)
University Project Officer: ………………………………….. Date: …………………………………..
4 | Stage 4: Tender/Building Contract Award | Date completed
4.1 | Confirm the F10 notification has been submitted to the Health and Safety Executive.(where required)
4.2 | Confirm there are arrangements in the tender documents for verifying the competence/adequacy of the proposed principal contractor and named specialist sub-contractors to carry out the project and manage the risks on site.
4.3 | Confirm there are arrangements in the tender documents for dealing with changes to the design and for cooperating with contractors.
4.4 | Confirm the pre-construction information, including relevant UCL safety rules and standards, has been provided to every contractor (or principal contractor) who may be appointed by UCL.
4.5 | Confirm the proposed program allows enough time for design, planning and construction including time for the contractor to plan and prepare for the work, and mobilise for the start of the construction phase.
4.6 | Confirm any residuals risks, sequencing of the construction process, phased handovers or assumptions is issued to the principal contractor within the tender documents, covering the construction, maintenance and demolition stages. (dependent upon the degree of risk identified within the project)
4.7 | Confirm the tender documents provide a project specific file contents list, taken from the project specification of works, and the arrangements for providing information and preparation of the Health and Safety File.
4.8 | Confirm the adequacy of the principal contractor’s construction phase plan (CPP), regarding compliance with CDM 2015 Regulations – planning, managing and monitoring the works and identifying and addressing risks to health and safety before they start on site. If the contractor has design responsibilities ensure that any safety implications of the design have been reflected on site in the CPP. | stage 5a
4.9 | Confirm that your contractor has made arrangements for adequate welfare facilities for their worker before the work starts. | stage 5a
Completion (signed off by)
University Project Officer: ………………………………….. Date: …………………………………..
5 | Stage 5: Mobilisation / Construction Period / Handover | Date completed
5.1 | Confirm that designers, including those engaged by the principal contractor and contractors who will carry out design work themselves, cooperate with each other, and designs meet the requirements of the Regulations.
5.2 | Confirm that the Principal Designer has taken reasonable steps to ensure cooperation between the permanent and any temporary works designers, in particular to make arrangements to ensure that designs are compatible and that the permanent works can support any loadings from temporary works.
5.3 | Confirm that the Principal Designer has attended site progress meeting(s) to monitor the satisfactory development of the health and safety file information, ensure the information is compliant and provide advice to the contractor as necessary to ensure the file is delivered prior to the handover date.
5.4 | Confirm that the Principal Designer has taken reasonable steps to ensure the provision of a suitable Health and Safety File at the handover date.
5.5 | Confirm the HSE F10 notification is up to date with programme and appointments.
5.6 | Confirm that on each occasion the Project team has visited site, they have observed site safety working practices and where necessary intervented with the contractor to prevent poor safety practices. These should be reported to the UPO and advise on any further action that is required.
Completion (signed off by)
University Project Officer: ………………………………….. Date: …………………………………..
Return to main page

## Value Engineering Report
Value Engineering Report
Return to main page
1. Project Information
Project Title | [6 empty] | Current Stage | [8 empty] | Access Control | RIBA Stage 1
Unique Project Reference | [6 empty] | UPO | [8 empty] | Brickwork | RIBA Stage 2
Building Name | [6 empty] | Date | [8 empty] | Concrete | RIBA Stage 3
2. Budget | [15 empty] | Decoration | RIBA Stage 5
LAB | [6 empty] | Cost Saving Achieved | 0 |  | A | 0 |  |  |  |  | Demolition | RIBA Stage 6
Pre-VE AFC | [6 empty] | Amount Remaining | 0 |  | B | 0 |  |  |  |  | Dry Lining | RIBA Stage 7
Cost saving required |  |  | 0 | [6 empty] | C | 0 |  |  |  |  | External Works
3. Value Engineering Options | [15 empty] | Flooring
Ref | Package | Description / Assumptions |  | A - Accepted | B - Pending | C - Rejected | Design Team Comments |  | Original Cost | Budget VE |  | Life Cycle Cost Implication | Life Cycle Cost Change (£) | Status | Action | Groundwork
Joinery
Lifts
MEPH
Metalwork
Piling
Precast
Roofing
Steelwork
Structural Timber
Other
|  |  |  | Total Saving | Total Saving | Total Saving |  |  |  | Total Saving
|  |  |  | 0 | 0 | 0 |  |  |  | 0
4. Final Approval
| Name and Position | [5 empty] | Signed
Engineering
Sustainability/Energy
Head Of Service
Strategy Manager
Project Sponsor

## Project Insurance Form
PROJECT INSURANCE FORM
Return to main page
This form is required only for Estates projects categorised as Medium or Large and is to be sent to UCL Legal to arrange appropriate project insurance.
Approval
Send this form to June Campbell in the Legal team and save to the Projects folders in Portfolio Services as part of the stage gate 4 documentation approval process. PLEASE NOTE: For Small Works projects/programme - if the total of all packages delivered within the small works project exceeds £100k, a seperate form must be submitted for each package.
To be completed by Legal Team
Legal team to include any additional insurance premium required to be charged to the project. Legal to send back this form to the UPO and cc the PSO.
Project Identity
Project Title |  | Unique Project Reference
UCL Project Officer (UPO) |  | Contract Award (SG4)
UPO Department |  | Construction Completion (SG5B)
Project Category |  | Contract Value
Building |  | Project Account Code (C0XXX)
Project Summary
Contractor Details
Contractor Name
Contractor Address
Form of contract | eg, GC Works 1, NEC3, JCT, etc
Completion (signed off by)
Project Officer: ………………………………….. Date: …………………………………..

## CH1
CH1 Form
Pre Contract Start Handover Form
Prior to handover to projects)
Contract Start Date:
Return to main page
Isolation Services
Have Isolation points been identified and meter readings taken?
|  | Comments | Initials | Date
Power | Y/N
Water | Y/N
Gas | Y/N
Other e.g. Compressed air, Medical gases, etc. | Y/N
Reusable Materials |  | Comments | Initials | Date
Have all reusable materials been removed & listed? | Y/N
Have all unwanted furniture etc. entered on WARP-IT, and for those not taken sufficient notice given to Soft Services to allow use elsewhere. (e.g.1 month minimum) | Y/N
Security |  | Comments | Initials | Date
Are security services to be maintained? If not, what other arrangements have been made? | Y/N
What arrangements have been made for site and vehicular access? | Y/N
Fire |  | Comments | Initials | Date
Have the UCL Fire Safety Manager / Fire Safety Officer been consulted with over the final designs? | Y/N
Have detailed discussions taken place on maintenance of existing fire strategy arrangements throughout the course of the project, particularly in respect of means of escape protection? | Y/N
Where there could be dusty works that may result in false alarms, have the UCL fire safety team been consulted with to ensure an appropriate strategy for temporary detection provision? | Y/N
Where necessary, has that strategy been implemented and recorded prior to commencement of works? | Y/N
Critical Areas |  | Comments | Initials | Date
Are there any services that need to be maintained within a work area i.e. feeds to critical areas? | Y/N
If so, have they been clearly identified? | Y/N
Waste |  | Comments | Initials | Date
Has all hazardous waste been removed by Facilities Waste Services? | Y/N
Have Laboratory cleanliness certificates been issued? | Y/N
Has a Site Waste Minimisation and Management Plan been prepared identifying ownership and responsibility and to be used to record weight, type and destination for each waste stream? Any reuse should be clearly identified in the SWMP. | Y/N
Asset Labelling |  | Comments | Initials | Date
Have all redundant asset labels been returned to EM&I | Y/N

## CH2
CH2 Form
Return to main page
Contacts
Main Contractor
Name:
Telephone number (office hours, 9-5):
Telephone number (out of hours):
Mobile:
EM & I Contact
Name:
Telephone number (office hours, 9-5):
Telephone number (out of hours):
Mobile:
Maintenance and Operations (MOT) Contract
Name:
Telephone number (office hours, 9-5):
Telephone number (out of hours):
Mobile:
Contacts for Miscellaneous Contractors
Name:
Telephone number (office hours, 9-5):
Telephone number (out of hours):
Mobile:
Circulate this to:
Security - Mark West, EM&I - Mark Lawrence, DL -TBA, CSC - Gary Pearson

## Project Tender Request
PROJECT TENDER REQUEST FORM
Return to main page
Project Identity
Contract Award Date (SG4) |  | Construction Completion Date (SG5)
Project Category |  | Contract Value
Building |  | Project Account Code
Project Summary - Scope of Works
Will scaffolding be required Yes / No
Tender Details
Tender Title
Proposed Return Date & Time
In-tend reference (Issued by Procurement Services)
Proposed Contract Period & Start Date
Pre-Tender Estimate
Companies to be invited to tender
| Company Name | Contact Name | Email & Contact Number
1
2
3
4
5
6
Other Key Stakeholders / Evaluators / Consultants relating to this tender
| Company Name | Contact Name | Email & Contact Number
1
2
3
4
5
6
Send this form to:
NB: Save in SG3 folder, email a copy to Contracts Management Office at estatescontracts@ucl.ac.uk and Portfolio Services Office at portfolioservices@ucl.ac.uk
Return to main page

## Tender Return Form
PROJECT TENDER RETURN FORM
Return to main page
To be completed by the Contracts Team on opening the tenders
Project Identity
Contract Award (SG4) |  | 0 |  |  | Construction Completion (SG5B) | 0
Project Category |  | 0 |  |  | Contract Value | 0
Building |  | 0 |  |  | Project Account Code | 0
Tender Details
Tender Title
Proposed Return Date & Time
In-tend reference (Issued by Procurement Services)
Proposed Contract Period & Start Date
Pre-Tender Estimate
Companies to be invited to tender (Non-OJEU)
| Company Name | Date | Time | Variant Value | Value
1
2
3
4
5
6
Tender opening witnessed by
Name
Signature
Name
Signature
Date
Time
Send this form to:
NB: Save in SG3 folder, email a copy to Contracts Management Office at estatescontracts@ucl.ac.uk and Portfolio Services Office at portfolioservices@ucl.ac.uk
Return to main page

## Project Request for LOI Form
REQUEST FOR LETTER OF INTENT FORM
Return to main page
A Letter of Intent is to be used only where it is essential that the contractor commences work before a formal contract has been agreed and signed by the parties.
Project Identity
Contract Title |  |  |  | Building Name (If appropriate)
UCL Project Officer (UPO) or Requestor |  | person requesting contract |  | Contract Award Date (SG4 or Start Date)
UPO Department |  |  |  | Contract End Date or construction Completion (SG5B/End Date)
Project Category |  | small/large/property |  | Contract Value
Purpose of LOI
e.g. to enter into a contract to : refurbish….., …...carry out a feasibility study….., …….provide a service to…..
Contractor Details
Contractor Name
Contractor Address
Form of contract | e.g., GC Works 1 , NEC3,JCT , UCL Service Agreement, Lease
Consultant/Solicitors Details - who has/will be producing the contract
Consultants/ Solicitors Name | e.g. UCL Legal, Potter Raper, Fenwick Elliott
Contact details
Return Date for signing/sealing | This should be no more than 2 weeks from LOI issue
Details to be included in LOI | Provide here the:-Key terms of the contract The total consideration Inc./ex VAT The limit on the amount to be paid pre-agreement completed under this LOI (usually reliminary/mobilisation costs only) Method of dispute resolution The UPO who is the instruction giver Liquidated and ascertained damages amount
Details Required
Parties | 1) UCL and 2)
Register of Interests Checked |  | Yes/No | Check the Register of Interests to ensure that there are no conflicts of interests
Contract to be Sealed? |  | Yes/No | Usually only for Property related Agreements
Approval Dates (Please insert all dates) |  | PRG
EMC
FC
Council
For approval send this form to:
NB: Save in your SG4 folder and email a copy to Contracts Management Office at estatescontracts@ucl.ac.uk and Portfolio Services Office at portfolioservices@ucl.ac.uk
Return to main page

## REQUEST TO ENTER CONTRACT
REQUEST FOR AUTHORISATION TO ENTER INTO A CONTRACT
Return to main page
Project Identity
Contract Award Date |  | 0 |  |  | Contract End Date or construction Completion | 0
Project Category |  | small/large/property |  |  | Contract Value | 0
Building Name (If appropriate) |  | 0 |  |  | Project Account Code | 0
Purpose of Contract
e.g. to enter into a contract to : refurbish….., …...carry out a feasibility study….., …….provide a service to…..
Contractor Details
Contractors Name
Contractor Address
Form of contract | e.g., GC Works 1 , NEC3,JCT , UCL Service Agreement, Lease
Consultant/Solicitors Details - who has/will be producing the contract
Consultants/ Solicitors Name | e.g. UCL Legal, Potter Raper, Fenwick Elliott
Contact details
Return Date for signing/sealing |  |  |  | This should be no more than 2 weeks from LOI issue or from submitting this request
Details Required
Parties | 1) UCL and 2)
Register of Interests Checked | Yes/No |  | Check the Register of Interests to ensure that there are no conflicts of interests
Contract to be Sealed? | Yes/No |  | (Only property related Contracts are likely to require sealing)
Approval Dates | PRG
(please insert all dates) | FC
FC
Council
Email this form to:
Contracts Management Office at estatescontracts@ucl.ac.uk and Portfolio Services Office at portfolioservices@ucl.ac.uk

## Fire Safety Handover Checklist
PROJECT FIRE SAFETY REQUIREMENTS - FIRE SAFETY HANDOVER CHECK LIST
UCL Projects (Rev 1 - Oct 2015)
Return to main page
Fire Safety Technical notes available to download from www.ucl.ac.uk/fire/documents
Fire Safety Systems: | Legislation & Standards: | Actioned or Submitted by & Date: | Received by & Date: | Maintenance Responsibility: | Certificates Provided & Stakeholder Approval Confirmed? | Comments / Defects
MEANS OF ESCAPE (MoE): | Fire Safety Order 2005
Escape Routes - are the escape routes from both the space and the premises been walked and found satisfactory? | Fire Safety Order 2005 |  |  | Project & Department | Yes / No / Not Applicable
Escape & Door Furniture - is the door furniture suitable (i.e. emergency type for Places of Assembly, where >60 persons using it etc.) easy to use, lock free where appropriate, suitable for the space/premises use? | Fire Safety Order 2005 |  |  | Project & Department | Yes / No / Not Applicable
Electronic Locks & Barriers - has Gallagher locks and barriers been interface & fitted with emergency release, green box overrides, witnessed & commissioned? | UCL Fire Safety Tech Note TN001 |  |  | Project and Access Systems | Yes / No / Not Applicable
FIRE COMPARTMENTATION: | Fire Safety Order 2005
Fire Doors - are they self-closing, been fitted with strips & seals, 1/2 leaves fitted with self closers, correctly signed, functional & suitable for location, occupants and traffic? | UCL Fire Safety Tech Note TN013 |  |  | Project & Department | Yes / No / Not Applicable
Passive Fire Protection & Fire Stopping - are all penetrations & structural supporting elements suitably fire protected, with a record of works provided? | UCL Fire Safety Tech Note MI06 &TN066 & ADB |  |  | Project & UCL Estates | Yes / No / Not Applicable
Fire Dampers - M&E surveyed and drop check completed? | Approved Document B - Building Regulations |  |  | Project & UCL Estates | Yes / No / Not Applicable
Fire Resisting Shutters - has correct fire rating been provided, is there warning of shutter activation/drop, is there clear markings around drop zone, has it been witnessed & commissioned? | Approved Document B - Building Regulations |  |  | Project & UCL Estates | Yes / No / Not Applicable
Fire Resisting Glazing - has Integrity (& Insulation where necessary) been provided to correct fire rating, and is 'Pyro' etching visible on all glass sheets? | Approved Document B - Building Regulations |  |  | Project & UCL Estates | Yes / No / Not Applicable
Service Risers - constructed to at least FR60 and all penetrations sealed, provided with FD30 doors signed 'fire door keep locked' & fitted with UCL Plant Room Keys? | Approved Document B - Building Regulations |  |  | Project & UCL Estates | Yes / No / Not Applicable
Electrical Switch Cupboards - do they meet FR30 & FD30(S) construction in sleeping accommodation, stairs enclosures & single escape conditions? | Approved Document B - Building Regulations |  |  | Project & UCL Estates | Yes / No / Not Applicable
FIRE ALARM (FA) SYSTEMS: | Fire Safety Order 2005
Fire Alarm System - any alterations and changes to the FA System been witnessed, commissioned & Certs' issued? | BS5839 Series / Fire Safety Tech Note TN54 & TN55 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
l FA Sounder Checks - has the sound pressure levels dB(A) been witnessed & recorded? | BS5839 Series / Fire Safety Tech Note TN54 & TN55 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
l FA Silent Tone Sounders - In BSUs, has Silent Tone sounders been fitted and sound pressure levels dB(A) witnessed & recorded? | BS5839 Series / Fire Safety Tech Note TN54 & TN59* |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
l FA Signal Interfaces - has fire, fault & pre-alarm signals to UCL Security Control (or ARC) been provided? | BS5839 Series / Fire Safety Tech Note TN54 & TN55 |  |  | Access Systems & Estates EM&I | Yes / No / Not Applicable
l FA Access Control Interfaces - on FA Activation has Gallagher controlled doors/barrier release been witnessed? | BS5839 Series / Fire Safety Tech Note TN001 |  |  | Access Systems & Estates EM&I | Yes / No / Not Applicable
l FA Access Control Interfaces - where fire doors fitted with Disabled/MIP opening devices, 'fail closed' on fire alarm activation & witnessed? | BS5839 Series / Fire Safety Tech Note TN002 |  |  | Access Systems & Estates EM&I | Yes / No / Not Applicable
l FA (Other Systems) Interfaces - lifts ground, fire suppression systems, roller shutters or curtains etc. where fitted, work correctly? | BS5839 Series / Fire Safety Tech Note TN54 & TN55 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
l FA FADE signs - where provided, correct locations, witnessed, commissioned & certs issued? | BS5839 Series / Fire Safety Tech Note TN54 & TN58 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
l FA Zones - are Zone Charts & Logbook provided & displayed? | BS5839 Series / Fire Safety Tech Note TN54 & TN55 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
l FA - Deaf Messaging System (DMS) Provided - where provided, witnessed, commissioned & certs issued? | BS5839 Series / Fire Safety Tech Note TN007 / TN54&5 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
EMERGENCY LIGHTING (EL): | Fire Safety Order 2005
Emergency Lighting System - has 3 hr test been completed, witnessed, commissioned & certs issued? | BS5266 Series / Fire Safety Tech Note TN020 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
l If addressable EL system - has a interface to BMS or other control system been provided, witnessed & tested? | BS5266 Series / Fire Safety Tech Note TN020 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
l If none-addressable EL units - has 3 hr test been completed, test keys been installed correctly system witnessed, commissioned & certs issued? | BS5266 Series / Fire Safety Tech Note TN020 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
FIRE BRIGADE EQUIPMENT: | Fire Safety Order 2005
Sprinklers - designed, installed and commissioned with certs issued, has UCL Insurer inspected an approved? | BS END 12845 & LPCB Sprinkler Installation Rules 2009 / TN038 |  |  | Access Systems & Estates EM&I | Yes / No / Not Applicable
Dry Rising & Fire Hydrant Systems - where provide, been witnessed, commissioned & certs issued? | Fire Safety Tech Note TN038 & BS9999 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
Smoke Control & Venting Systems – where provided, been witnessed, commissioned & certs issued? | Fire Safety Tech Note TN038 & BS9999 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
Firefighting Lift Provision - where provided, been witnessed, commissioned & certs issued? | Fire Safety Tech Note TN038 & BS9999 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
Prescribed Voltage Electrical Equipment – where provided, have fireman's switches been witnessed, commissioned & certs issued? | Fire Safety Order 2005 (Article 37) & TN039 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
Fume Cupboards (Fireman's Switch) - where provided have been correctly installed, witnessed, commissioned & certs issued? | UCL Fire Safety Tech Note TN038 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
Containment Level 3 Labs (Fireman's Switch) - where provided have been correctly installed, witnessed, commissioned & certs issued? | UCL Fire Safety Tech Note TN038 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
AHU & Heating Controls - have they been interfaced to close down & auto-restart after fire alarm activation, witnessed & commissioned? | UCL Fire Safety Tech Note TN038 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
FIRE EXTINGUISHERS SYSTEMS: | Fire Safety Order 2005
Portable Fire Extinguishers - correct type provided and installed? | BS5306 Series / Fire Safety Tech Note TN023 |  |  | UCL Fire Safety Manager | Yes / No / Not Applicable
Fire Hose Reels - any works or changes to systems witnessed, commissioned & certs issued? | BS5306 Series / Fire Safety Tech Note TN038 |  |  | UCL Fire Safety Manager & EM&I | Yes / No / Not Applicable
Fire Gas Suppression Systems - any works or changes to systems been witnessed, commissioned & certs issued? | BS5306 Series / Fire Safety Tech Note TN038 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
Fume Cupboard (Fire Suppression) – where provided, has the correct system & been witnessed, commissioned & certs issued? | UCL Fire Safety Tech Note TN038 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
Hypoxic Atmosphere Suppression Systems - any works or changes to systems witnessed, commissioned & certs issued? | BS5306 Series / Fire Safety Tech Note TN038 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
DISABLED / MOBILITY IMPAIRED PERSONS (MIP) FACILITIES: | Fire Safety Order 2005
Disabled Refuges - communications provided witnessed and commissioned | BS 5839-9 / BS9999 / ADB |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
Evacuation Lift Provision - where provided, been witnessed, commissioned & certs issued? | Fire Safety Tech Note TN038 & BS9999 |  |  | Project & UCL Estates EM&I | Yes / No / Not Applicable
FIRE SAFETY SIGNS: | Fire Safety Order 2005
Fire Action Notices (FAN) - provided? | UCL Fire Safety Tech Note TN090 |  |  | UCL Fire Safety Manager | Yes / No / Not Applicable
General Fire Safety Signs - provide? | UCL Fire Safety Tech Note TN090 |  |  | UCL Fire Safety Manager | Yes / No / Not Applicable
FIRE SAFETY STAFF FAMILIARISATION: | Fire Safety Order 2005
Occupying staff - has occupying staff received fire safety familiarisation of the space or building prior to occupation | Fire Safety Order 2005 & Fire Tech Note MI03 |  |  | UCL Project & Fire Safety Managers | Yes / No / Not Applicable
NOTES:

## Sustainability
CH3 - Sustainability
Return to main page
Unique Project Ref | Project Title | Building | UCL Project Officer (UPO) |  | Approval | Date
0 | 0 | 0 | 0 | Liz Lee | 0 | 0
Utilities and Sustainability | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Details of any gas, electric and/or water meters removed, installed or replaced provided to the ES team (including reference, MPAN, MPRN, location on building plan) | Gas and electricity meter regulations 2014 |  |  | Contractor | Y/N
Energy design calculations achieved / information for DEC’s / EPC’s | Building Regulations part L; Energy Performance of Buildings Regulations |  |  | Contractor | Y/N
Incumbent utility provider notified of meter changes where used for billing purposes |  |  |  | Project Manager | Y/N
Details of any incumbent utility supplier been provided to the ES team. NO NEW CONTRACTS TO BE AGREED |  |  |  | Project Manager | Y/N
End/start of supply readings been taken and provided |  |  |  | Contractor and Project Manager (agreed with ES team) | Y/N
SWMP confirms application of waste hierarchy on site | Waste Regulations |  |  | Contractor | Y/N
Waste volumes, types and method of disposal recorded and provided to the ES team | UCL Sustainable Design Standard |  |  | Contractor | Y/N
Meter readings for all utilities taken and provided monthly for 1 year following handover | UCL Sustainable Design Standard |  |  | Contractor | Y/N
Has energy data been added to Carbon Buzz for all new builds and any major refurbishments? | UCL Sustainable Design Standard |  |  | M&E consultant or Project Manager | Y/N
Has appropriate signage been provided to ensure that building users know how to operate elements of the building, e.g. lighting and HVAC controls? | UCL Sustainable Design Standard |  |  | Contractor in consultation with ES team | Y/N
Has a building user guide been provided? Content to include information on local HVAC and lighting controls, energy and water efficient features, security and access, furniture, space use, cycle storage, and the principles of design and operation. | UCL Sustainable Design Standard |  |  | Contractor | Y/N
Commissioning data for all renewables provided |  |  |  | Contractor | Y/N
Meter readings for all renewables taken and provided monthly for 1 year following handover | UCL Sustainable Design Standard |  |  | Contractor | Y/N
All meters linked to BMS | UCL Sustainable Design Standard |  |  | Contractor | Y/N
Demonstration of BMS interface to ensure correct operation. |  |  |  | Contractor | Y/N
Number of cycle parking spaces available to new building users provided to the ES team | UCL Sustainable Design Standard |  |  | Architect or Project Manager
Environmental certification issued and displayed (where applicable) | BREEAM; Ska |  |  | Contractor or Environmental Consultant

## Water Systems
CH3 - Water Systems Checklist
Return to main page
Water Systems | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Water distribution systems, and flushing, cleaning and chemical dosing certificates | BS 6700 |  |  |  | Y/N
Legionella risk assessment records | Legionnaire’s Disease. The Control of Legionella Bacteria. Approved Code of Practice and Guidance |  |  |  | Y/N
Water Risk Assessment produced or updated |  |  |  |  | Y/N
Copy of notification to local authorities of installation of wet cooling towers and evaporative condensers | Notification of Cooling Towers and Evaporative Condensers Regulations 1992 |  |  |  | Y/N
Chemical and bacteriological test results for drinking water cisterns greater than 1000 litres (not a statutory requirement) | Workplace (Health, Safety and Welfare) Regulations 1992: BS 6700 |  |  |  | Y/N
Chlorination certificate(s) for drinking water (not a statutory requirement) | Workplace (Health, Safety and Welfare) Regulations 1992: BS 6700 |  |  |  | Y/N
Source protection policy and licence to use water supplied by a borehole | National Rivers Authority |  |  |  | Y/N
Water authority discharge of waste certificate | Water Authority and National Rivers Authority |  |  |  | Y/N
Water hygiene maintenance & inspection regime in place |  |  |  |  | Y/N
Closed systems dosing details |  |  |  |  | Y/N
List of any Water features on site that would require management (RA) |  |  |  |  | Y/N
Essential spare parts list for site stores |  |  |  |  | Y/N
Microbiological examination of water systems – test report |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N
Water pressure test. Mains cold water & District Hot Water |  |  |  |  | Y/N

## Mechanical Systems
CH3 - Mechanical Systems Checklist
Return to main page
Mechanical Systems | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Heating system test certificates |  |  |  |  | Y/N
Pressure systems test certificates | HSC L122 |  |  |  | Y/N
Pressure vessels and systems written schemes of examination | HSC L122 |  |  |  | Y/N
Pipework systems test certificates | HVCA TR/6 & TR/20 |  |  |  | Y/N
Gas Appliance and/or Boiler details |  |  |  |  | Y/N
Boiler Commissioning data |  |  |  |  | Y/N
Update Gas drawing showing appliance loading |  |  |  |  | Y/N
Gas infrastructure drawings amended |  |  |  |  | Y/N
Medical gas systems Commissioning data |  |  |  |  | Y/N
Air compressors Commissioning data |  |  |  |  | Y/N
Have all gas scavenging systems been tested & certificated. |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N
Essential spare parts list for site stores |  |  |  |  | Y/N

## Lifts
CH3 - Lifts
Return to main page
Lifting Systems | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Escalator test certificate | Format suggested in HSE Guidance Note PM45 |  |  |  | Y/N
Escalator reports of thorough examination | BS 5266 Part 1 |  |  |  | Y/N
Lift installation type test certificates for locking devices, governors, buffers, and doors | BS 5655 Part 10 |  |  |  | Y/N
Lift maker’s high voltage test certificates | BS 5655 Part 10 |  |  |  | Y/N
Lift installation test certificates | BS 5655 Part 10 |  |  |  | Y/N
Lifting equipment reports of thorough examination | HSE form F2530 |  |  |  | Y/N
Lifting Beams |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N
Essential spare parts list for site stores |  |  |  |  | Y/N

## AC & Ventilation
CH3 -A/C and Ventilation
Return to main page
A/C & Ventilation Systems | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Air-con system test certificates |  |  |  |  | Y/N
Inventory of refrigerants ie F-Gas register | Control of Substances Hazardous to Health Regulations 2002: Environmental Protection Act 1990 |  |  |  | Y/N
Air-con system performance testing results and certificates |  |  |  |  | Y/N
Ventilation systems test certificates |  |  |  |  | Y/N
Chiller Commissioning data |  |  |  |  | Y/N
Local Exhaust Ventilation commissioning and certification |  |  |  |  | Y/N
Air conditioning inspection and certification (over 250kw) |  |  |  |  | Y/N
Filtration details |  |  |  |  | Y/N
Hazardous areas ie BSU or Cat 3 Lab |  |  |  |  | Y/N
Essential spare parts list for site stores |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N
Specialised equipment (define fume cupboards) |  |  |  |  | Y/N

## Building Fabric
CH3 -Building Fabric
Return to main page
Building Fabric | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Has building control officer visited the completed works? | Building Control Cert |  |  |  | Y/N
Has Asbestos Register been updated |  |  |  |  | Y/N
Drainage system test certificates | Approved Document H |  |  |  | Y/N
Drainage infrastructure drawing amended |  |  |  |  | Y/N
Attain declaration relating to asbestos presence within the building and modify asbestos register |  |  |  |  | Y/N
Update Asbestos Database inc CAD drawings |  |  |  |  | Y/N
Automatic door commissioning certification |  |  |  |  | Y/N
Roof access |  |  |  |  | Y/N
Update Roof survey database |  |  |  |  | Y/N
Gutter cleaning |  |  |  |  | Y/N
Tiered seating inspection |  |  |  |  | Y/N
Moveable wall inspection |  |  |  |  | Y/N
Fire door inspections |  |  |  |  | Y/N
Provision of finishes schedule ie decoration, floor finish, ceilings etc |  |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Painting |  |  |  |  | Y/N
Details of Manholes, access ways etc. |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N
Essential spare parts list for site stores |  |  |  |  | Y/N

## Electrical Systems
CH3 -Electrical Systems
Return to main page
Electrical Systems | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Records of tests carried out on electrical appliances (not a statutory requirement to keep copy of records) | Electricity at Work Regulations 1989 |  |  |  | Y/N
Electricity infrastructure drawings amended |  |  |  |  | Y/N
All circuits have been tested in accordance with the IEE codes of practice and results recorded including insulation resistance, continuity. | NICECI Certification |  |  |  | Y/N
High level lighting details & Lux level tests |  |  |  |  | Y/N
Street lighting Lux level tests |  |  |  |  | Y/N
Lightning protection systems | BS EN/IEC 62305 |  |  |  | Y/N
Generators Commissioning data |  |  |  |  | Y/N
UPS Commissioning data |  |  |  |  | Y/N
PV (solar) generation |  |  |  |  | Y/N
Switchgear manufacturers certificates |  |  |  |  | Y/N
Meter details |  |  |  |  | Y/N
PA systems |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N
Essential spare parts list for site stores |  |  |  |  | Y/N

## Facilities
CH3 Facilities
Return to main page
Facilities Systems | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Record of waste disposal | Environmental Protection Act 1990 |  |  |  | Y/N
Landscape design plan for the site to scale 1:200 is the preferred scale |  |  |  |  | Y/N
List of Tree Preservation Orders |  |  |  |  | Y/N
Copy of the roads and car parks design and surface area m2 for gritting |  |  |  |  | Y/N
Topographical survey data in respect of slopes - mowing |  |  |  |  | Y/N
Disabled access for special treatment (gritting + Salt Box) |  |  |  |  | Y/N
Has a full builders clean been completed? |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N
Have windows been cleaned |  |  |  |  | Y/N
Essential spare parts list for site stores |  |  |  |  | Y/N

## Security
CH3 Security
Return to main page
Security Systems | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Security alarm test certificates |  |  |  |  | Y/N
Have keys/cards that have been issued to the contractor been returned? |  |  |  |  | Y/N
Access control system installation certification | BS 7274 Part 4 |  |  |  | Y/N
CCTV system test certificates | BS EN 501342-7 |  |  |  | Y/N
Have all head-end systems been programmed correctly with site plans etc.? |  |  |  |  | Y/N
Additional Guarding requirements |  |  |  |  | Y/N
Have as-built system drawings been submitted to UCL security? |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N

## BMS
CH3 BMS
Return to main page
BMS Control Systems | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
BMS strategy document provided |  |  |  |  | Y/N
BMS front end software updated and timetables set |  |  |  |  | Y/N
Have Graphics been set up and proved |  |  |  |  | Y/N
Have all links been proved & witnessed |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N
Have any software licences been handed over |  |  |  |  | Y/N
Essential spare parts list for site stores |  |  |  |  | Y/N

## Miscellaneous
CH3 Miscellaneous Systems
Return to main page
Miscellaneous Systems | Legislation and Standards | Actioned or Submitted by and Date | Receieved by and Date | Maintenance Repsonsibility | Is Maintenance Satisfactory? | Comments / Defects
Has an Asset register been produced & all assets labelled with EQ Nos | UCL Data Collection Form |  |  | To be listed on Asset Collection sheet, unless specified below | Y/N
Fall arrest system – maintenance / inspection regime |  |  |  |  | Y/N
Fall arrest systems – LOLER inspection |  |  |  |  | Y/N
Eye bolt detals |  |  |  |  | Y/N
Noise assessment records | Control of Noise at Work Regulations 2005 |  |  |  | Y/N
COSHH Assessments of any hazardous materials handed over |  |  |  |  | Y/N
Record drawings for building services installation | Section 2 and 6 of the Health and Safety at Work Act 1974 |  |  |  | Y/N
Building services operating and maintenance information including emergency procedures | Section 2 and 6 of the Health and Safety at Work Act 1974: Construction (Design and Management)Regulations 2007, Building Regulations Part L2 2006 |  |  |  | Y/N
Risk assessment records for plant and systems | Management of Health and Safety at Work Regulations 1999 (if not already covered by COSHH Regulations |  |  |  | Y/N
Documentation for Wayleaves and adopted roads | Occupier information on any possible public right of way access or responsibility for highway repairs to roads and footpaths adjacent to property |  |  |  | Y/N
Energy design calculations achieved / information for DEC’s / EPC’s |  |  |  |  | Y/N
Confined Spaces – Safe system of work |  |  |  |  | Y/N
Documentation regarding any special designation ‘Conservation Area’ |  |  |  |  | Y/N
Have Draft O&M’s (Health & Safety File) been produced |  |  |  |  | Y/N
Has all equipment been demonstrated & necessary staff trained |  |  |  |  | Y/N