**Relationship between workpackages in Quality and Effectiveness of Supported Tenancies for people with mental health problems (QuEST) research programme**

**WP1**

Adapt the quality indicator (QuIRC) and Client’s Assessment of Treatment Scale (CAT) via focus groups with staff and service users.

*Project month 1-12*

**WP2**

Survey nationally representative sample of 90 supported accommodation services. Interviews with managers (using adapted QuIRC) and 450 service users.

*Project month 13-30*

**WP3**

Qualitative interviews with 30 staff and 30 service users of supported accommodation services.

*Project month 13-30*

**WP2**

Prospective study of 30 month outcomes for 450 users of supported accommodation services surveyed.

*Project month 45-60*

**WP4**

Pilot trial to assess feasibility of comparing two forms of supported accommodation. Will incorporate findings from WP2 and WP3 on service predictors of better clinical outcomes and aspects of care that staff and service users consider most beneficial. Qualitative interviews with 10 staff and 10 SUs.

*Project month 31-60*

Project month 31-60